## Slide 1: Quantifying anomalies in patients with neuropathologies via diffusion Magnetic Resonance Imaging. (Application to Alzheimer diagnosis)
Nicolas Indriets

## Slide 2: Preprocessing and model update
Brain mask dilated sub-106 without reslice
Brain mask dilated sub-106 with reslice
Problem solved, but still have some subjects where eddy does not work (It takes too much time to compute). Use of a variable in the study to take that into account

## Slide 3: Atlas mapping
Area to analyse to answer my research questions :
Parahippocampal cortex
Enthorinal cortex
Posterior cingulate cortex
Isthmus cingulate cortex
Amygdala
Hippocampus
Baseline :
Uncinate fasciculus
First Method :
Register the Desikan-Killiany atlas on a T1 image in MNI152 space
Create the atlas with the labels file
Register patients with the T1 image and the first volume of white matter ODF
Apply the transform on the atlases.
Second method :
Register patients with a FA map of HCP1065 for XTRACT atlas and FA map obtained with DTI
Apply the transform on the atlases

## Slide 4: Atlas mapping
Desikan-Killiany Atlas
Registered and mapped atlas on sub-009

## Slide 5: Atlas mapping
XTRACT HCP Probabilistic Tract Atlas
Registered and mapped atlas on sub-009

## Slide 6: Study

## Slide 7: Study
DTI : AD, RD, FA, MD
Diamond : wAD, wRD, wFA, wMD, fractions of fibers
MF : wfvf, fvf_tot
Noddi : fiso, fintra, fextra, ODI

## Slide 8: Timeline
2023
Today
Dec
Jan
Feb
Mar
Apr
May
Jun
2022
2023
Preprocessing
Dec 13 - Feb 28
State of the art writing
Feb 13 - Mar 20
Study of the microstructure of the CB
Feb 13 - Mar 20
Comparison with PET tau
Apr 1 - Apr 30
Writing of the master thesis
Mar 20 - Jun 2
Mar 20 - Mar 31
Comparison with the literature
State of the art
Mar 20
Analysis
Apr 30
Master thesis complete
Jun 2
Progress made on the state of the art -> To continue
Start the statistical analysis of microstructure